## Sheet1
Date | DesignatedvRole | Detail Responsibillity | TeamvMamber
|  |  | Toshi | Pasha | Candise
Week3 | Team Leader | Weekly Report | x
| Database/Back-end Develop | Create ERD | x | x | x
|  | Create tables and fields using MySQL | x | x | x
|  | Insert Sample Data |  | x | x
Middle-Wave Developer
Fron-End Developer
Week4 | Team Leader | Weekly Report |  | x
| Database/Back-end Develop | Continuous improvement | x
| Middle-Wave Developer | access to the database |  | x | x
| Fron-End Developer | Webpage design | x | x | x
|  | Home Page, Navigation | x
Week5 | Team Leader | Weekly Report |  |  | x
| Database/Back-end Develop | Continuous improvement |  | x
| Middle-Wave Developer | store the customer information | x
| Fron-End Developer | Account Creation Page |  | x
|  | Account Inoformation Page |  |  | x
Week6 | Team Leader | Weekly Report | x
| Database/Back-end Develop | Continuous improvement |  |  | x
| Middle-Wave Developer | Choose the destination, hotel, flight… |  | x | x
| Fron-End Developer | DIY Trip Page | x
|  | Pre-Packaged Trip Page |  | x
Week7 | Team Leader | Weekly Report |  | x
| Database/Back-end Develop | Continuous improvement |  |  | x
| Middle-Wave Developer | Change content in the cart | x | x
| Fron-End Developer | Order list/information Page |  |  | x
Week8 | Team Leader | Weekly Report |  |  | x
| Database/Back-end Develop | Continuous improvement |  |  | x
| Middle-Wave Developer | Order list/information generation | x
| Fron-End Developer | Payment Page |  | x
Week9 | Team Leader | Weekly Report | x
| Database/Back-end Develop | Continuous improvement |  | x
| Middle-Wave Developer | Paypal Application | x |  | x
| Fron-End Developer | Continuous improvement
Week10 | Team Leader | Weekly Report |  |  | x
| Database/Back-end Develop | Continuous improvement | x
| Middle-Wave Developer | Continuous improvement |  | x
| Fron-End Developer | Continuous improvement |  |  | x